## Sheet1
ID | Name | Start Date | End Date | Duration | Progress % | Dependency | Details | Color
26 | Task 5 | 2023-11-30 08:00 | 2023-12-14 17:00 | 15 days | 74 |  | We need to give the games a website structure, where people can play these games and also able to find the solutions after a certain time of their interaction with the game. They could also see their progress in the game as well. | 241
27 | Error fixing suggested by QA team | 2023-11-30 08:00 | 2023-12-02 17:00 | 3 days | 100 |  | The development team will start work on fixing the bugs which are found by Q/A team. Also if there are any suggestions the development team will do them as well. | 31
28 | Games website | 2023-12-03 08:00 | 2023-12-06 17:00 | 4 days | 100 | 27FS | Here we will combine all the tasks and make a complete website for it. The website will be hosted for people to play game on it. This website will also be used for study purposes as well. Students can learn from the ideas being implemented in this project. | 121
30 | User sign in and game progress | 2023-12-07 08:00 | 2023-12-09 17:00 | 3 days | 100 | 28FS | Make a sign up and sign in page for the users. The users will sign in to the website and their score/progress will be stored by the website as well. | 121
29 | Puzzle levels | 2023-12-10 08:00 | 2023-12-13 17:00 | 4 days | 30 | 30FS | Make puzzles inside the games. There should be some levels being introduced in the games as well, so that the user who wants to play it as a game could enjoy it. | 121
31 | Finalize github repository | 2023-12-14 08:00 | 2023-12-14 17:00 | 1 day | 0 | 29FS | Finalize the github repoistory and get feedback from teammates. Make the updated version of the app repository available on github. | 241
32 | Submit milestone | 2023-12-14 17:00 | 2023-12-14 17:00 | 0 days | 0 | 31FS | The team will submit the milestone on 15 december. | 241