## Sheet1
ID | Name | Start Date | End Date | Duration | Progress % | Dependency | Resources | Color
1 | Project Plan | 2023-10-09 08:00 | 2023-10-24 17:00 | 16 days | 100 |  | Aman Thapa Magar - Coding/Overseer,Jawad Nasar Shah - DB/Timeline,Junkai Ou - Coding/Quality Assurance and Testing,Mya Lwin - Coding/Quality Assurance and Testing/Documentation,Rimjhim Chakraborty - Document/Quality Assurance and Testing/Coding,Rohan Kadam - Project Leader,Tom Naccarato - Coding/Documentation,Veerpal - Document/Quality Assurance and Testing
2 | Setting up github | 2023-10-09 08:00 | 2023-10-12 17:00 | 4 days | 100 |  | Aman Thapa Magar - Coding/Overseer,Jawad Nasar Shah - DB/Timeline,Junkai Ou - Coding/Quality Assurance and Testing,Mya Lwin - Coding/Quality Assurance and Testing/Documentation,Rimjhim Chakraborty - Document/Quality Assurance and Testing/Coding,Rohan Kadam - Project Leader,Tom Naccarato - Coding/Documentation,Veerpal - Document/Quality Assurance and Testing | 121
3 | n-queen simple web application | 2023-10-13 08:00 | 2023-10-17 17:00 | 5 days | 100 | 2FS | Aman Thapa Magar - Coding/Overseer,Rohan Kadam - Project Leader | 211
4 | Make it interactive | 2023-10-18 08:00 | 2023-10-24 17:00 | 7 days | 100 |  |  | 301
5 | Bug Fixes | 2023-10-18 08:00 | 2023-10-20 17:00 | 3 days | 100 | 3FS | Jawad Nasar Shah - DB/Timeline,Aman Thapa Magar - Coding/Overseer,Rohan Kadam - Project Leader | 331
6 | Interaction of user with application | 2023-10-21 08:00 | 2023-10-24 17:00 | 4 days | 100 |  | Rimjhim Chakraborty - Document/Quality Assurance and Testing/Coding,Rohan Kadam - Project Leader,Tom Naccarato - Coding/Documentation | 301
7 | Graphics Design | 2023-10-21 08:00 | 2023-10-24 17:00 | 4 days | 100 |  |  | 301
8 | Kanoodle_App | 2023-10-25 08:00 | 2023-11-13 17:00 | 20 days | 98
9 | Managment and Timeline | 2023-10-25 08:00 | 2023-10-25 17:00 | 1 day | 100 |  | Jawad Nasar Shah - DB/Timeline,Rohan Kadam - Project Leader | 91
10 | Search for possible solutions | 2023-10-26 08:00 | 2023-10-28 17:00 | 3 days | 100 | 9FS | Aman Thapa Magar - Coding/Overseer,Junkai Ou - Coding/Quality Assurance and Testing
11 | Implement algorithm | 2023-10-29 08:00 | 2023-11-08 17:00 | 11 days | 100 | 10FS | Aman Thapa Magar - Coding/Overseer,Tom Naccarato - Coding/Documentation
12 | Front end | 2023-11-05 08:00 | 2023-11-08 17:00 | 4 days | 100 |  | Junkai Ou - Coding/Quality Assurance and Testing,Mya Lwin - Coding/Quality Assurance and Testing/Documentation | 181
13 | Database creation and implementation | 2023-11-05 08:00 | 2023-11-08 17:00 | 4 days | 100 |  | Jawad Nasar Shah - DB/Timeline | 271
14 | Connecting to font-end and db | 2023-11-09 08:00 | 2023-11-11 17:00 | 3 days | 100 | 13FS,12FS | Aman Thapa Magar - Coding/Overseer,Tom Naccarato - Coding/Documentation
15 | Testing and Q/A | 2023-11-12 08:00 | 2023-11-13 17:00 | 2 days | 80 | 14FS | Rimjhim Chakraborty - Document/Quality Assurance and Testing/Coding,Veerpal - Document/Quality Assurance and Testing,Jawad Nasar Shah - DB/Timeline | 31