## Sheet1
ID | Name | Start Date | End Date | Duration | Progress % | Dependency | Details | Color
16 | Kanoodle 3rd Solver (Task 4) | 2023-11-14 08:00 | 2023-11-30 08:00 | 16 days | 100 |  | Make the kanoodle app in a 3d pyramid shape | 241
18 | 3D background and research | 2023-11-14 08:00 | 2023-11-17 17:00 | 4 days | 100 |  | Do some research about how to change the existing app to 3D or to make a new one from start. Know how to achieve the task 4 and what algorithms to use | 241
19 | Implement Algorithm | 2023-11-18 08:00 | 2023-11-21 17:00 | 4 days | 100 | 18FS | Implement Donald Knuth algorithm. X solutions yet to be verified | 271
20 | User Interactive UI | 2023-11-20 08:00 | 2023-11-23 17:00 | 4 days | 100 | 18FS+2 days | The UI should be made interactive using Three.js and orbitalcontrol.js. These are the javascript libraries used to show the work done on python django algorithm. | 211
21 | Test the code and app | 2023-11-24 08:00 | 2023-11-26 17:00 | 3 days | 100 | 20FS | Testing should be completed in three days and if any review of code we will have time to complete that during the testing period | 331
22 | code review and changes | 2023-11-25 08:00 | 2023-11-27 17:00 | 3 days | 100 | 21SS+1 day | Code review and changes should go on after the testing is started | 211
23 | Documentation | 2023-11-25 08:00 | 2023-11-28 17:00 | 4 days | 100 | 21SS+1 day | Documentation is started during the testing period as most of the code here is already completed. Testing at this time should only be done for bug fixes, so a documentation of the task should also be completed before the milestone. | 301
25 | Mile stone (Task 4) | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 days | 0 | 23FS+1 day | Milestone for the task 4 should be completed on 30. We will complete task 4 by then and will try to start on task 5 from there on. | 301